## Example
Alminawi.com ... Tools Thru Tales; From Story to Strategy: Practical Tools for Sociotechnical Leaders.
Tool: | Risk Register
Tale Link: | The Lighthouse Keeper’s Ledger & Risk Register – Tools Thru Tales
Fictitious Critical Path for Project ??? | [16 empty] | 58 | 13 | 70
Assumed project activities: A-O | [17 empty] | L
S = Start | [10 empty] | 38 | 10 | 47 | 48 | 10 | 57 | 295 | 237 | 307
E = End | [11 empty] | E |  |  | G
Update the start & activity durations, and observe e the results | [10 empty] | 262 | 224 | 271 | 272 | 224 | 281 | 58 | 11 | 68 | 69 | 8 | 76 | 77 | 7 | 83
[5 empty] | 35 | 1 | 35 | 36 | 2 | 37 | [7 empty] | I |  |  | M |  |  | N
[6 empty] | B |  |  | C | [7 empty] | 282 | 224 | 292 | 293 | 224 | 300 | 301 | 224 | 307
[5 empty] | 131 | 96 | 131 | 132 | 96 | 133
|  | 1 | 34 | 34 | [6 empty] | 134 | 69 | 202 | 203 | 50 | 252 | 253 | 49 | 301 | [6 empty] | E
| S |  | A | [8 empty] | F |  |  | H |  |  | K
|  | 169 | 168 | 202 | [6 empty] | 134 | 0 | 202 | 203 | 0 | 252 | 253 | 0 | 301 | 302 | 6 | 307
O
[5 empty] | 35 | 87 | 121 | 122 | 12 | 133 | [9 empty] | 302 | 0 | 307
[6 empty] | D |  |  | J
[5 empty] | 203 | 168 | 289 | 290 | 168 | 301